## G_Data centres A
United Utilities - Data Centres A
| Company | United Utilities
| Enhancement area | Data Centres A
| PCD No. | PCDWA_UUWGS
| Common requirements | See "Price Control Deliverables" section of UUW004
Additional company specific requirements
| Description | None
| Output measurement and reporting | None
| Conditions on scheme | None
| Assurance | None
| Non-delivery PCD payment | Unit | Payment rate
| Stage 1A – New clarification treatment process - [✂ REDACTED] | Per site £m | 53.5044
| Stage 2C – [✂ REDACTED] | Per site £m | 7.5301
| Stage 2D – [✂ REDACTED] | Per site £m | 5.4375
| Stage 2B – [✂ REDACTED] | Per site £m | 4.7408
| Stage 2A – [✂ REDACTED] | Per site £m | 5.8948
| Stage 2E – production capacity upgrades | Per site £m | 14.4075
| Time incentives PCD payment | Unit | Payment rate
| n/a | n/a | n/a
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Stage 1A – New clarification treatment process - [✂ REDACTED] | No. of sites | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Stage 2C – [✂ REDACTED] | No. of sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Stage 2D – [✂ REDACTED] | No. of sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Stage 2B – [✂ REDACTED] | No. of sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Stage 2A – [✂ REDACTED] | No. of sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Stage 2E – production capacity upgrades | No. of sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1

## G_Data centres B
United Utilities - Data Centres B
| Company | United Utilities
| Enhancement area | Data Centres B
| PCD No. | PCDWB_UUWGS
| Common requirements | See "Price Control Deliverables" section of UUW004
Additional company specific requirements
| Description | None
| Output measurement and reporting | None
| Assurance | None
| Conditions on scheme | None
| Non-delivery PCD rate | Unit | Under-performance
| Spend on data centre pipeline connections delivered (Stage 1B): | £m per 1% completion | 0.67889
| Spend on network reinforcement (pipes) delivered (Stage 2F): | £m per 1% completion | 0.17297
| Spend on network reinforcement (pumping stations) delivered (Stage 2G): | £m per 1% completion | 0.022406
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance (Stage 1B): | % | 0 | 0 | 0 | 0 | 11.37 | 62.16 | 100 | 100 | 100 | 100 | 100 | 100
| Spend on scheme as a % of allowance (Stage 2F): | % | 0 | 0 | 0 | 0 | 9.88 | 70.56 | 93.21 | 100 | 100 | 100 | 100 | 100
| Spend on scheme as a % of allowance (Stage 2G): | % | 0 | 0 | 0 | 0 | 9.88 | 70.56 | 93.21 | 100 | 100 | 100 | 100 | 100

## G_Clean Energy
United Utilities - Clean Energy
| Company | United Utilities
| Enhancement area | Clean Energy
| PCD No. | PCDW3_UUWGS
| Common requirements | See "Price Control Deliverables" section of UUW006
Additional company specific requirements
| Description | None
| Output measurement and reporting | None
| Assurance | None
| Conditions on scheme | None
| Non-delivery PCD rate | Unit | Under-performance
| Spend on Clean Energy schemes delivered: | £m per 1% completion | 2.5101
| Time incentives PCD rate | Unit | Under-performance | Out-performance
| N/A | N/A | N/A | N/A
| PCD outputs (cumulative) | Unit | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Spend on scheme as a % of allowance | % | 0 | 0 | 0 | 0 | 9.66 | 36.74 | 69.96 | 97.23 | 100 | 100 | 100 | 100
| Ml/d capacity | Ml/d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 49 | 49 | 49 | 49

## G_STWs
United Utilities - PR24 Growth at STWs
| Company | United Utilities
| Enhancement area | PR24 Growth at STWs
| PCD No. | PCDWW27_UUWGS
| Common requirements | See "Price Control Deliverables" section of UUW008
Additional company specific requirements
| Description | None
| Output measurement and reporting | None
| Assurance | None
| Conditions on scheme | None
| Non-delivery PCD rate | Unit | Scheme type | Outlier type | Outlier efficiency | Reason for outlier | Added Process Capacity in PE | Expected change in DWF permit (M3/D) | Ammonia permit change dummy (<3 mg/l) | Change in FFT permit l/s | Allowance pre adjustments (£m) | AMP 8 adjustment factor | DWF compliance adjustment value | Post AMP8 and DWF adjustment allowance | Other adjustment factor | Post adjustments and FS and RPEs allowance
| [✂ REDACTED] | £m |  |  |  |  | 856 | 317.8084 | [7 empty] | 5.1181
| [✂ REDACTED] | £m |  |  |  |  | 71 | 65.9215 | [7 empty] | 2.7462
| [✂ REDACTED] | £m |  |  |  |  | 268 | 13.5259 |  | 2.76 | [5 empty] | 3.2947
| [✂ REDACTED] | £m |  |  |  |  | 2849 | 116.0917 | 1 | [6 empty] | 13.325
| [✂ REDACTED] | £m |  |  |  |  | 324 | 40.2006 | [7 empty] | 3.4914
| [✂ REDACTED] | £m |  |  |  |  | 1847 | 526.919 | [7 empty] | 6.7113
| [✂ REDACTED] | £m |  |  |  |  | 93 | 5.5934 | [7 empty] | 2.6821
| [✂ REDACTED] | £m |  |  |  |  | 45 | 14.5278 | [7 empty] | 2.442
| [✂ REDACTED] | £m |  |  |  |  | 809 | 101.5019 |  | 18.19 | [5 empty] | 5.386
| [✂ REDACTED] | £m |  |  |  |  | 18288 | 485.8794 | 1 | [6 empty] | 25.7266
| [✂ REDACTED] | £m |  |  |  |  | 74 | 1.0192 |  | 0.85 | [5 empty] | 2.7351
| [✂ REDACTED] | £m |  |  |  |  | 16393 | 89.7068 |  | 27.03 | [5 empty] | 20.1285
| [✂ REDACTED] | £m |  |  |  |  | 2183 | 641.4647 | [7 empty] | 7.295
| [✂ REDACTED] | £m |  |  |  |  | 233 | 240.0236 |  | 7.39 | [5 empty] | 4.2503
| [✂ REDACTED] | £m |  |  |  |  | 18 | 7.4824 | [7 empty] | 2.1724
| [✂ REDACTED] | £m |  |  |  |  | 184 | 7.7738 |  | 0.98 | [5 empty] | 3.2602
| [✂ REDACTED] | £m |  |  |  |  | 774 | 4.747 | [7 empty] | 4.1265
| [✂ REDACTED] | £m |  |  |  |  | 227 | 302.6148 |  | 8.11 | [5 empty] | 4.4163
| [✂ REDACTED] | £m |  |  |  |  | 12409 | 4724.8667 | [7 empty] | 23.0859
| [✂ REDACTED] | £m |  |  |  |  | 71 | 3.1559 | [7 empty] | 2.5624
| [✂ REDACTED] | £m |  |  |  |  | 115 | 55.7212 |  | 0.81 | [5 empty] | 2.942
| [✂ REDACTED] | £m |  |  |  |  | 22 | 0.24669 | [7 empty] | 2.1846
| [✂ REDACTED] | £m |  |  |  |  | 136 | 22.8957 | [7 empty] | 2.9152
| [✂ REDACTED] | £m |  |  |  |  | 40 | 0.88942 |  | 2.48 | [5 empty] | 2.5427
| [✂ REDACTED] | £m |  |  |  |  | 4036 | 2253.263 |  | 63.13 | [5 empty] | 15.2997
| [✂ REDACTED] | £m |  |  |  |  | 84 | 50.4335 |  | 3.38 | [5 empty] | 3.0273
| [✂ REDACTED] | £m |  |  |  |  | 42 | 31.4233 | [7 empty] | 2.4681
Sites and proposed allowance to be included in PR29 PCD:
| Non-delivery PCD rate | Unit | Scheme type | Outlier type | Outlier efficiency | Reason for outlier | Added Process Capacity in PE | Expected change in DWF permit (M3/D) | Ammonia permit change dummy (<3 mg/l) | Change in FFT permit l/s | Allowance pre adjustments (£m) | AMP 8 adjustment factor | DWF compliance adjustment value | Post AMP8 and DWF adjustment allowance | Other adjustment factor | Post adjustments and FS and RPEs allowance
| [✂ REDACTED] | £m |  |  |  |  | 649 | 104.1458 | 3 | [6 empty] | 4.2579
| [✂ REDACTED] | £m |  |  |  |  | 1265 | 376.4139 | [7 empty] | 5.7544
| [✂ REDACTED] | £m |  |  |  |  | 62 | 11.0553 |  | 0.53 | [5 empty] | 2.6918
| [✂ REDACTED] | £m |  |  |  |  | 340 | 32.5107 | 1 | [6 empty] | 7.9805
| [✂ REDACTED] | £m |  |  |  |  | 17589 | 5119.8365 |  | 450.24 | [5 empty] | 40.3031
| [✂ REDACTED] | £m |  |  |  |  | 8271 | 2133.7565 | [7 empty] | 14.6561
| [✂ REDACTED] | £m |  |  |  |  | 25831 | 9613.0842 |  | 540.92 | [5 empty] | 57.4182