## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR111 GWE_WOODFORD | Author | [✂] (UU Environmental Planner, PLE)
Date: | 10/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | Stockport Chesire East
Planning permission | Yes
Environmental Impact Assessment (EIA) | Screening Opinion required - low risk
Abstraction Licence | Variation on existing licence
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 2 | Planning permission will be required for any new buildings including kiosks over 29m3 within UU operational land [✂]. Risk of land purchase [✂]. An EIA screening opinion will be required for new water treatment facilities [✂] and possibly refurbishment works to the existing pipeline route depending on scope. Risk of An EIA being required is considered low.
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designation: Hazel Grove WTW and Woodford BHs are located within an area of designated Greenbelt. Visual impact will be a prime concern. | Refer to Constraints tab and Environmental Review Plan
2 | Trees & Hedgerows | Yes | There are trees and hedgerows at the Woodford BH site and at various locations along the existing pipeline route. If there are any impacts to trees and hedgerows there will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
3 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Potentially | None identifed at Hazel Grove WTW or Woodford BHs. Impacts to amenity spaces along the pipeline route should be avoided where possible.
4 | Access land - Village Green, Common Land, Millennium Greens etc. | No
5 | Heritage and Archaeology | Yes | An archaelogical desk based assessment will be required with possible further investigations and mitigation measures.
6 | Tree Preservation Order | No
7 | Public Right of Way | Yes | The existing pipeline route crosses several Public Rights of Way. Depending on the scope of works PRoW closures may be required if these are to be diverted or closed during the construction phase.
8 | Main Rivers | Yes | The existing pipeline route crosses Lady Brook which is a designated Main River. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency will be required.
9 | Ordinary Watercourses | Yes | The existing pipeline route crosses several ordinary watercourses. Any works which impact on these and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
10 | Flood Risk Zone | Yes | The existing pipeline route is within Flood Risk Zones 2 and 3 at Lady Brook. Any works outside of Flood Zone 1 a will require a Flood Risk Assessment to accompany the Planning Application and Flood Risk Activity Permit (if required).
11 | EIA Screening Opinion | Yes | An EIA Screening Opinion will be required due to the nature and scale of the proposed development.
12 | Environmental Impact Assessment | Potentially | The outcome of the Screening Opinion will determine if an EIA is required to support the planning application. Although it is considered to be low risk, if one is required this will add signficant time and cost onto the programme.
13 | Planning Permission | Yes | Planning permission will be required for at least some elements of the new WTW. Dependent on the scope of the pipeline works there may be planning requirements for accesses to serve the construction sites. In the event that an EIA is required all Permitted Development Rights would be withdrawn and Planning Permission would be required for the overall scheme.
14 | Discharge Permit | Potentially | Any new discharge would require a permit from the EA
15 | Abstraction Licence | Potentially | Any amendments to existing abstraction licences would require a licence from the EA.
Yes
No
Potentially
Note on A2: Rimmer, Tom: • If any aspect is affected/potentially affected set this out in this section and provide brief details of the constraint/requirement and any reference for future Information for Tenderers (IfT). • If unaffected click “no” and this aspect will not appear in the next tab…

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Hazel Grove Constraints
Hazel Grove WTW | Local Plan
EA Flood Risk Map | Tree Preservation Order Check
[✂] | [✂]
Public Rights of Way

## Woodford BHs
Woodford BHs | Local Plan
EA Flood Risk Map | Tree Preservation Order Check
Public Rights of Way
[✂]

## Environmental Review Plan
[✂]