## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR 107a GWE_AUGHTON PARK a2 | Author | [✂] (UU Environmental Planner, PLE)
Date: | 10/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | West Lancashire
Planning permission | Yes
Environmental Impact Assessment (EIA) | Low risk in isolation but If considered in conjuntion with WR107b risk would increase.
Abstraction Licence | Yes - there are no existing abstraction licences in place at Moss End or Aughton Park BHs
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 1 | Due to the length of the pipeline route an EIA screening opinion will be required. The likelihood of an EIA being required is low, however, it may need to be considered in conjunction with WR107b. This would increase the risk of an EIA . If an EIA is required this will add significant time and cost onto the programme. In this event all permitted development rights are withdrawn for below ground works and planning permission will be required for the overall scheme. Early external consultation will be required with third parties including land owners and the LPA before the exact routeing of the pipeline is confirmed. As there are no abstraction licences in place [✂] early consultation will be required with the Environment Agency. The lead time for a new licence can be up two years.
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designations: The proposed works at Moss End, Aughton Park, Royal Oak and the pipeline route are located within an area of designated Green Belt. Visual Impact will be a prime concern. Stautory Designated Sites: None. | Refer to Constraints tab and Environmental Review Plan
3 | Trees & Hedgerows | Yes | Trees and hedgerows are located within and in close proximity to the working areas including groups of TPO trees that should be avoided. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
4 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Potentially | Impacts to amenity spaces should be avoided where possible.
5 | Access land - Village Green, Common Land, Millennium Greens etc. | No | Impacts to access land should be avoided where possible
6 | Heritage and Archaeology | Yes | An archaelogical desk based assessment would be required with possible further investigations and mitigation measures.
| Tree Preservation Order | Potentially | There are TPO trees within the vicinity of the pipeline route. These should be avoided where possible.
7 | Public Right of Way | Yes | The pipeline route will impact Public Rights of Way. PRoW closures will be required if these are to be diverted or closed during the construction phase.
8 | Main Rivers | Yes | The pipeline route crosses Knoll Brook which is a designated main river. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency and Natural England will be required.
9 | Ordinary Watercourses | Yes | The pipeline route crosses ordinary watercourses. Any works which impact on these and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
| Flood Risk Zone | No
16 | EIA Screening Opinion | Yes | The development proposals exceeds the thresholds set out in Schedule 2 of the Town and Country Planning (Environmental Impact Assessment) Regulations 2017 and as such an EIA Screening Opinion will need to be submitted to West Lancashire Borough Council. the scheme should also be considered in conjuntion with WR107b.
17 | Environmental Impact Assessment | Yes | The outcome of the Screening Opinion would determine if an EIA is required. The likelihood of an EIA being required is low, however, if this scheme is to be considered in conjunction with WR107b the risk is increased. If an EIA is required this will add significant time and cost onto the programme.
18 | Planning Permission | Yes | Planning permission wouldbe required for any new buildings over 29m3, any plant or machinery over 15m high on UU operational land and any new accesses. In the event that an EIA is required all Permitted Development Rights would be withdrawn and Planning Permission would be required for the overall scheme.
29 | Discharge Permit | Potentially | Any new discharges would require a permit from the Environment Agency.
30 | Abstraction Licence | Potentially | Any new or varied abstractions would require an Abstraction Licence obtained from the Environment Agency.
Yes
No
Potentially
Note on A2: Rimmer, Tom: • If any aspect is affected/potentially affected set this out in this section and provide brief details of the constraint/requirement and any reference for future Information for Tenderers (IfT). • If unaffected click “no” and this aspect will not appear in the next tab…
Note on C16: Watson, Dave (Planning): should this be potentially
Note on D19: Watson, Dave (Planning): check if abstractions within exisiting limits or need to change or are new

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Environmental Review Plan
[✂]

## Constraints
Satellite Image | Aughton Park |  | Moss End
[✂] | [✂] |  | [✂]
EA Flood Risk Map |  | TPO Check
[✂] |  | [✂]
PROW Check |  | Local Plan
[✂] |  | [✂]