## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR106b GWE_WALTON_2 | Author | [✂] (UU Environmental Planner, PLE)
Date: | 23/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | Warrington Halton
Planning Permission | Yes
Environmental Impact Assessment (EIA) | Screening Required - Moderate Risk
Abstraction Licence | Existing Abstraction - increase abstraction within LicQ
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 2 | An EIA screening opinion will be required. There is a moderate risk that an EIA will be required to support the planning application which will add significant time and cost onto the programme. In this event all permitted development rights are withdrawn and planning permission will be required for the overall scheme. The proposed location for a new [✂] facility at Appleton [✂] is located within a rural area and designated Greenbelt. Visual impact will be a prime concern.
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designations: The majority of the working areas are within Greenbelt including the new [✂] location at Appleton. Visual Impact will be a prime concern. Stautory Designated Sites: None. | Refer to Constraints tab and Environmental Review Plan
3 | Trees & Hedgerows | Yes | Trees and hedgerows are located within and in close proximity to the proposed WTW location and pipeline route. There are TPO trees close to the Halton and Daresbury [✂] sites. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
4 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Potentially | Impacts to amenity spaces should be avoided where possible.
5 | Access land - Village Green, Common Land, Millennium Greens etc. | No
6 | Heritage and Archaeology | Yes | An archaelogical desk based assessment will be required with possible further investigations and mitigation measures.
| Tree Preservation Order | Potentially | There are TPO trees close to Daresbury and Halton [✂] sites which shoud be avoided where possible. Permission will be required from the LPA if works to TPO trees are required.
7 | Public Right of Way | Yes | The pipeline route will impact Public Rights of Way. PRoW closures will be required if these are to be diverted or closed during the construction phase.
8 | Main Rivers | No
9 | Ordinary Watercourses | Yes | The pipeline route crosses ordinary watercourses. Any works which impact on these and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
| Flood Risk Zone | No
16 | EIA Screening Opinion | Yes | The development proposals exceeds the thresholds set out in Schedule 2 of the Town and Country Planning (Environmental Impact Assessment) Regulations 2017 and as such an EIA Screening Opinion will need to be submitted to Halton and Warrington Councils.
17 | Environmental Impact Assessment | Potentially | There is a moderate risk of an EIA being required to support the planning application. This will add significant time and cost onto the programme.
18 | Planning Permission | Yes | Planning permission would be required for any large kiosks/buildings, plant and machinery over 15m high on UU operational land and any new accesses. Permitted development rights will in effect be removed if the development requires EIA.
29 | Discharge Permit | Yes | Any new discharge permits should be confirmed with the Environment Agency.
30 | Abstraction Licence | No
Yes
No
Potentially
Note on A2: Rimmer, Tom: • If any aspect is affected/potentially affected set this out in this section and provide brief details of the constraint/requirement and any reference for future Information for Tenderers (IfT). • If unaffected click “no” and this aspect will not appear in the next tab…

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Constraints
Appleton Res & Halton BHs |  | Pipeline route area
EA Flood Risk Map |  | Tree Preservation Order Check
[✂] |  | Warrington | Halton
|  | [✂] | [✂]
Public Rights of Way |  | Local Plan
[✂] |  | [✂]
Warrington | Halton |  |  | Halton
[✂] | [✂] |  |  | [✂]

## Environmental Review Plan
[✂]