## G2 STT IEA Annex 3
Topic | Receptor | Activity and impact (construction and operation phases) | Embedded mitigation | Additional mitigation | Uncertainties / further information required | Risk RAG Rating
Biodiversity | Berwyn and South Clwyd Mountains SAC | Vyrnwy Bypass pipeline - potential construction disturbance and air quality impacts however site sufficiently distanced that no impacts anticipated Vyrnwy Reservoir direct release - the SAC is not hydrologically connected downstream of the proposed regulation release. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA)) | Not applicable, no impact pathway.
Biodiversity | Berwyn SPA | Vyrnwy Bypass pipeline - potential construction disturbance and air quality impacts however site sufficiently distanced that no impacts anticipated Vyrnwy Reservoir direct release - operation of releases from Vyrnwy Reservoir will not lead to any changes to the baseline water environment in the vicinity of the SPA. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA)) | Not applicable, no impact pathway.
Biodiversity | Bredon Hill SAC | Deerhurst to Culham (Interconnector) pipeline - potential construction air quality impacts however site sufficiently distanced that no impacts anticipated. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Chilterns Beechwoods SAC | Deerhurst to Culham (Interconnector) pipeline - potential construction air quality impacts however site sufficiently distanced that no impacts anticipated; no qualifying features are water dependent and no operational impacts are anticipated. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Cothill Fen SAC | Deerhurst to Culham (Interconnector) pipeline - potential construction air quality impacts however site sufficiently distanced that no impacts anticipated; no construction impacts on underlying aquifer groundwater levels; no operational impacts are anticipated as site is not downstream the outfall site. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Cotswold Beechwoods SAC | Netheridge WwTW discharge diversion - no operational impacts as not hydrologically connected downstream of the Netheridge discharge location and no water dependant species. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Dixton Wood SAC/SSSI | Deerhurst to Culham (Interconnector) pipeline - potential construction disturbance and air quality impacts and loss of functionally linked habitat (broadleaved deciduous woodland) could potentially occur during construction, although it is concluded that woodland present in the footprint of the works may not be suitable habitat for violet click beetle. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Best practice construction measures Air Quality - Well maintained, modern plant to be used to minimise emissions. Dust will be controlled through dampening haul roads and earthworks and aggregate processing plant. | Discussions with NE to agree additional mitigation measures. | Confirmation of methods employed to install pipeline to determine extent of potential air quality impacts Limited records available for of violet click beetle and uncertainty over dispersal dynamics of violet click beetle
Biodiversity | Hartslock Wood SAC | Deerhurst to Culham (Interconnector) pipeline - potential construction air quality impacts however site sufficiently distanced that no impacts anticipated; no operational impacts as none of the qualifying features have been identified as water dependent. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Little Wittenham SAC | Deerhurst to Culham (Interconnector) pipeline - potential construction air quality impacts however site sufficiently distanced that no impacts anticipated; site is not hydrologically connected to the River Thames and no operational impacts are anticipated. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Montgomery Canal SAC | Vyrnwy Bypass pipeline - potential construction air and water quality impacts however site sufficiently distanced that no impacts anticipated Vyrnwy Reservoir direct release - no direct hydrological connectivity between the proposed bypass pipeline route or from the reservoir release and the Montgomery Canal and no operational impacts anticipated. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Midland Meres and Mosses Phase 1 Ramsar | Vyrnwy Bypass pipeline / Shrewsbury redeployment - potential construction pollution, disturbance and air quality impacts however site sufficiently distanced Vyrnwy Reservoir direct release - operation of releases from Vyrnwy Reservoir will not lead to any changes to the baseline water environment in the vicinity of the SPA; not hydrologically dependent on the River Vyrnwy or River Severn so no operational impacts anticipated. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Midland Meres and Mosses Phase 2 Ramsar | Vyrnwy Bypass pipeline - risk of changes to the hydrological regime/ groundwater supply to site and exposure to pollution incidents if the pipeline is installed at a depth where groundwater is present and hydrologically connected to site; not hydrologically dependent on the River Vyrnwy or River Severn so no operational impacts anticipated. Impact pathway deemed unlikely due to distance from Midland Meres and Mosses Phase 2 Ramsar (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Best practice construction measures Water quality - All vehicles and any chemical/ oil storage will be fully bunded to prevent any accidental pollution of groundwater or watercourses. Hydrology/ groundwater - The pipeline route will have a number of major crossings including rivers. Mitigation measures including the use of trenchless crossings will be adopted to minimise impacts. Sections of the route will also be within the flood plain where high groundwater levels are soil permeability are expected. Adequate methods of construction will be adopted to minimise the impact to groundwater. | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Midland Meres and Mosses Phase 2 Ramsar | Shrewsbury redeployment - potential construction pollution incidents and invasive species and non-native species spread however site sufficiently distanced; not hydrologically dependent on the River Severn so no operational impacts anticipated. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | River Clun SAC | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for Atlantic salmon which may impact on the number of juveniles salmonids in the watercourse which contribute to the lifecycle of freshwater pearl mussel. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3
Biodiversity | River Dee and Bala Lake SAC | Vyrnwy Bypass pipeline - potential construction pollution, disturbance and air quality impacts however site sufficiently distanced and outside of the same catchment; no operational impacts no identified hydrological connectivity. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | River Usk SAC | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for migratory species. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3
Biodiversity | River Wye SAC | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for migratory species. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3
Biodiversity | Severn Estuary SAC | All STT components (operation of supported or unsupported STT) - potential impacts associated with flow changes on migration, reproduction and supporting habitat for migratory fish (freshwater life stages) and supporting habitats of the Severn Estuary however changes in flow (including pass forward flow into the estuary) and the resulting changes in velocity, depth and water level will be within the interannual variations that would be observed under baseline conditions. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Severn Estuary SAC | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for migratory species and/or on supporting habitats of the Severn Estuary. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3
Biodiversity | Severn Estuary SAC | Vyrnwy Bypass pipeline - potential for construction phase direct mortality and injury of ammocoetes if present, loss of functionally linked habitat, noise, visual and vibration disturbance, spawning habitat deterioration via localised increases in suspended sediment from bank erosion. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Best practice construction measures Tunnel or directional drilling over main rivers where possible Minimise removal of riparian vegetation (avoid damage to bank stability, minimise habitat loss). If necessary to remove, reinstate riparian vegetation. Minimise duration of any necessary in-channel working to avoid compaction, disruption of flow processes, bank erosion Minimise impacts on water quality through temporary fluming watercourses, buffer strips, straw bales to stop sediment from the site compounds running off-site untreated. Construction mitigation relating to fine sediment runoff and spills and leaks management to be included as defined as part of any environmental permit applications and may require some route re-alignment. Timing of in-channel works to avoid key periods of upstream migration and spawning for twaite shad, river lamprey and sea lamprey. | Discussions with NE to agree additional mitigation measures. | Confirmation of implementation of all mitigation measures. Fish habitat surveys at the outfall location to determine if suitable silt beds are present for lamprey ammocoetes.
Biodiversity | Severn Estuary SAC | Deerhurst to Culham (Interconnector) pipeline - potential construction phase impacts on functionally linked habitat for qualifying fish (e.g. siltation and deposition, impedance of movement, entrapment and impingement, noise and vibration disturbance, salinity regime changes and temperature changes). (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Best practice construction measures Air quality - Well maintained plant to be used. Plant will be modern and in good condition to minimise emissions. Dust will be controlled through dampening haul roads and earthworks and aggregate processing plant. Water quality - Measures will be taken to protect any temporary exposure of bare soil from runoff during heavy rainfall events. Earthworks drainage will be controlled including use of temporary settlement ponds. All vehicle and chemical/ oil storage will be fully bunded to prevent any accidental pollution of groundwater or watercourses. The mitigation measures will be set out in the applications for Flood Defence Consents where these are required for any river construction works. Noise - Construction working hours will be limited as agreed during the planning process. Plant to be used will be modern and in good condition with silencers fitted when near to key noise receptors. Any landscaping bunds around perimeter at permanent sites will be provided at the start of construction (which can provide noise barrier benefits). | Discussions with NE to agree additional mitigation measures. | Confirmation of implementation of all mitigation measures.
Biodiversity | Severn Estuary SPA | All STT components (operation of supported or unsupported STT) - potential impacts associated with flow changes supporting habitats of the Severn Estuary however changes in flow (including pass forward flow into the estuary) and the resulting changes in velocity, depth and water level will be within the interannual variations that would be observed under baseline conditions. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Severn Estuary SPA | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on supporting habitats of the Severn Estuary. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes.
Biodiversity | Severn Estuary SPA | All STT components (operation of supported or unsupported STT) - potential construction phase pollution, disturbance and air quality impacts on supporting habitat; potential direct effects on supporting habitat (coastal and floodplain grazing marsh). (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Best practice construction measures | See also Severn Estuary SAC specification Construction works to avoid the wintering season from November – March. If construction works must be conducted during the wintering season to avoid nesting birds, an Ecological Clerk of Works is recommended to undertake a bird survey prior to works to ensure no birds are present within 200m of the works. If present, works must stop until the qualifying species have exited the construction area. Use of fitting silencers/ noise dampening equipment, screening and maintenance of a buffer zone via an Ecological Clerk of Works to prevent adverse effects on qualifying birds, particularly teal that may be present in large numbers. Coastal and floodplain grazing marsh priority habitat to be reinstated where possible. Discussions with NE to agree additional mitigation measures. | Confirmation of implementation of all mitigation measures. Wintering surveys in the vicinity of the Deerhurst intake and Interconnector pipeline route to determine species presence and movement from feeding and roosting grounds. WeBS site River Severn – Hawk Bridge to Tewkesbury which is within the footprint of the interconnector intake and pipeline, survey data only publicly available for 2019/20.
Biodiversity | Severn Estuary Ramsar | All STT components (operation of supported or unsupported STT) - potential impacts associated with flow changes on migration, reproduction and supporting habitat for migratory fish (freshwater life stages) and supporting habitats of the Severn Estuary however changes in flow (including pass forward flow into the estuary) and the resulting changes in velocity, depth and water level will be within the interannual variations that would be observed under baseline conditions. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Severn Estuary Ramsar | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for migratory species and/or on supporting habitats of the Severn Estuary. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3
Biodiversity | Severn Estuary Ramsar | All STT components (operation of supported or unsupported STT) - potential construction phase impacts (suspended sediment (siltation and deposition), salinity regime changes and temperature changes, potential invasive and non-native species introduction/ spread from construction vehicles and unclean PPE, noise and vibration disturbance, entrapment and impingement and potential water pollution incidents). (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Best practice construction measures | See also Severn Estuary SAC specification Construction works to avoid the wintering season from November – March. If construction works must be conducted during the wintering season to avoid nesting birds, an Ecological Clerk of Works is recommended to undertake a bird survey prior to works to ensure no birds are present within 200m of the works. If present, works must stop until the qualifying species have exited the construction area. Use of fitting silencers/ noise dampening equipment, screening and maintenance of a buffer zone via an Ecological Clerk of Works to prevent adverse effects on qualifying birds, particularly teal that may be present in large numbers. Coastal and floodplain grazing marsh priority habitat to be reinstated where possible. Discussions with NE to agree additional mitigation measures. | Confirmation of implementation of all mitigation measures. Wintering surveys in the vicinity of the Deerhurst intake and Interconnector pipeline route to determine species presence and movement from feeding and roosting grounds. WeBS site River Severn – Hawk Bridge to Tewkesbury which is within the footprint of the interconnector intake and pipeline, survey data only publicly available for 2019/20.
Biodiversity | Tanat and Vyrnwy Bat sites SAC | Shrewsbury redeployment - potential construction noise, light and vibration disturbance, fragmentation of foraging habitat, air pollution and pollution incidents from construction vehicles however site sufficiently distanced; no operational impacts as none of the qualifying features have been identified as water dependent. (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Walmore Common SPA | Netheridge WwTW discharge diversion - no operational impacts as negligible impacts on hydrological regime are anticipated within the Severn Estuary (offsite supporting habitat). (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Walmore Common Ramsar | Netheridge WwTW discharge diversion - no operational impacts as negligible impacts on hydrological regime are anticipated within the Severn Estuary (offsite supporting habitat). (see STT-G2-S3-121-Informal Habitats Regulation Assessment (HRA) Annex) | Not applicable, no impact pathway.
Biodiversity | Grafton Lock Meadows SSSI | Deerhurst to Culham (Interconnector) pipeline - construction impacts, disruption to groundwater flows/levels as vegetation within site is driven by groundwater levels (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Pipeline optimisation informed by habitat mapping and condition surveys. Discussions with NE to agree additional mitigation measures. | Need for understanding of distribution of interest features across site, habitat and condition survey. Improve understanding of hydrological connectivity. Need to complete SSSI assessment with detailed design information.
Biodiversity | Chimney Meadows SSSI | Deerhurst to Culham (Interconnector) pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Turvey’s Piece SSSI | Deerhurst to Culham (Interconnector) pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Dixton Wood SSSI | Deerhurst to Culham (Interconnector) pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Lark Wood SSSI | Deerhurst to Culham (Interconnector) pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Morton Pool and Pasture SSSI | Vyrnwy Bypass pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Llanymynech Llynclys Hills SSSI | Vyrnwy Bypass pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Croft Mills Pasture SSSI | Vyrnwy Bypass pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site . (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Sweeney Fen SSSI | Vyrnwy Bypass pipeline - construction air quality impacts / noise disturbance, not considered likely to be significant given distance to site. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Best practice construction measures | Discussions with NE to agree additional mitigation measures. | N/A
Biodiversity | Rectory Farm Meadows SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Avon; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Upham Meadow and Summer Leasow SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Avon; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Guy’s Cliffe SSSI | All STT components (operation of supported or unsupported STT) - no water dependent ecological features, no operational impacts anticipated. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Not applicable, no impact pathway.
Biodiversity | Racecourse Meadows SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Avon; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Welford Field SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Avon; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Tiddesley Wood SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Avon; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Severn Ham, Tewkesbury SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Severn; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Old River Severn, Upper Lode SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Severn; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment) | Operation of STT solution as defined at Gate 2 | N/A | Uncertainty over whether changes to the scheme will have adverse effects to site if changes to the scheme identify potential for changes in river levels
Biodiversity | Upper Severn Estuary SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within the Severn Estuary; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Severn Estuary SSSI | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within the Severn Estuary; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Ancient woodland | Deerhurst to Culham (Interconnector) pipeline - pipeline construction related direct impacts (area near Guiting Woods located adjacent working area) and construction air quality/noise disturbance. | Best practice construction measures. Tree surveys to be undertaken prior to construction to assist tree retention. Protection requirements to be identified to ensure the final pipeline route avoids unnecessary removal of trees, hedgerows or other important vegetation. Soils are to be stored and reinstated following construction to maintain seedbanks. | Review pipeline routing to avoid encroachment of habitat Restrict construction area working widths informed by habitat surveys. Discussions with NE to agree additional mitigation measures. | Tree and woodland habitat surveys.
Biodiversity | Priority habitats – coastal floodplain grazing marsh | Deerhurst to Culham (Interconnector) pipeline - pipeline construction related direct impacts within pipeline and intake working areas (loss of habitat); potential for disruption of localised surface and groundwater flows to support habitat; construction water quality impacts; habitat deterioration (e.g. soil compaction). | Best practice construction measures | Review pipeline routing to avoid encroachment of priority habitat. Pipeline/working area optimisation informed by habitat mapping and condition surveys. Detailed design to ensure depth of pipe does not impede flow during operational phase. Avoid construction during winter to avoid disrupting grazing marsh flood events. Habitat reinstatement following construction. Restore natural drainage following construction. Discussions with NE to agree additional mitigation measures. | Need for habitat mapping along pipeline route. Detailed hydrogeological studies to inform pipeline routing and depth.
Biodiversity | Priority habitats – traditional orchards; lowland meadows, lowland calcareous grassland; deciduous woodland | Deerhurst to Culham (Interconnector) pipeline - pipeline construction related direct impacts within pipeline and intake working areas (loss of habitat); construction phase effects (air quality impacts / noise disturbance) | Best practice construction measures | Review pipeline routing to avoid encroachment of priority habitat, and construction working areas to avoid deterioration during detailed design (to be informed by habitat surveys). Consider tunnelling for sections of route which goes through priority habitat. Habitat reinstatement following construction (if required). Discussions with NE to agree additional mitigation measures. | Need for habitat mapping along pipeline route.
Biodiversity | Priority habitats – coastal floodplain grazing marsh | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Severn or River Avon; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Priority habitats – Lowland Fens | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Severn; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Priority habitats – purple Moor grass and rush pastures | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Severn; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Priority habitats – wet woodland | All STT components (operation of supported or unsupported STT) - potential changes in flow are not considered discernible and will not impact on the water dependent habitats as there is not predicted to be a significant change in water level or velocity within impacted reaches of the River Severn; no adverse effects from water quality identified. (see STT-G2-S3-117-Protected Habitat Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Protected species - fish | All STT components (operation of supported or unsupported STT) - potential impacts on egg incubation, migration, spawning/nursery/feeding habitat on fish species within the River Severn and tributaries from changes in flow, velocity, depth. (see SSTT-G2-S3-114-Fisheries Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Protected species - fish | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for migratory species within the River Severn and tributaries. (see STT-G2-S3-114-Fisheries Assessment Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | N/A | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3. For potential olfactory inhibitors in fish, it is recognised that the commercially available limit of detection may be altogether too high to draw conclusions.
Biodiversity | Protected species - fish | All STT components (operation of supported or unsupported STT) - potential impacts on migration, spawning/juvenile/feeding habitat, and direct impacts on fish species within the River Thames and tributaries from changes in flow, velocity, depth and changes in weir pool habitats. (see SSTT-G2-S3-114-Fisheries Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | Collection of bathymetry and hydraulic data under suitable flow conditions at selected weir pool reaches on the River Thames for inclusion in a 2D model.
Biodiversity | Protected species - fish | Vyrnwy Bypass pipeline - construction water quality impacts / noise & vibration disturbance. | Best practice construction measures Tunnel or directional drilling over main rivers where possible Minimise removal of riparian vegetation (avoid damage to bank stability, minimise habitat loss). If necessary to remove, reinstate riparian vegetation. Minimise duration of any necessary in-channel working to avoid compaction, disruption of flow processes, bank erosion Minimise impacts on water quality through temporary fluming watercourses, buffer strips, straw bales to stop sediment from the site compounds running off-site untreated. Construction mitigation relating to fine sediment runoff and spills and leaks management to be included as defined as part of any environmental permit applications and may require some route re-alignment. Timing of in-channel works to avoid key periods of upstream migration and spawning for twaite shad, river lamprey and sea lamprey. | Discussions with NE to agree additional mitigation measures. | Confirmation of implementation of all mitigation measures. Fish habitat surveys at the outfall location to determine if suitable silt beds are present for lamprey ammocoetes.
Biodiversity | Protected species - fish | Deerhurst to Culham (Interconnector) pipeline - construction water quality impacts / noise & vibration disturbance. | Best practice construction measures Air quality - Well maintained plant to be used. Plant will be modern and in good condition to minimise emissions. Dust will be controlled through dampening haul roads and earthworks and aggregate processing plant. Water quality - Measures will be taken to protect any temporary exposure of bare soil from runoff during heavy rainfall events. Earthworks drainage will be controlled including use of temporary settlement ponds. All vehicle and chemical/ oil storage will be fully bunded to prevent any accidental pollution of groundwater or watercourses. The mitigation measures will be set out in the applications for Flood Defence Consents where these are required for any river construction works. Noise - Construction working hours will be limited as agreed during the planning process. Plant to be used will be modern and in good condition with silencers fitted when near to key noise receptors. Any landscaping bunds around perimeter at permanent sites will be provided at the start of construction (which can provide noise barrier benefits). | Directional/ baffled lighting during works on the riverbank will minimise light disturbance on the River Severn. Consider the use of alternative piling rigs required and/or soft starts during the construction to reduce noise and vibration. Avoiding any night-time working within the channel and scheduling construction works to avoid continuous work with the main river channel. Avoid open-cut crossings of minor watercourses during upstream migration period for Atlantic salmon, European eel and lamprey. Avoid and/or minimise construction works between October-May. Construction compounds will be sited sensitively and a buffer from designated habitats and sensitive receptors is to be maintained. All habitats should be reinstated after constructions. A rehabilitation plan should be developed by a suitably qualified ecologist and should include the reinstatement of site draining in habitats that are depended on the movement of groundwater. Spoil from pipeline construction should be distributed across the construction easement before topsoil replacement. The approach to reinstatement of habitats should be included in the Construction Environmental Management Plan Vehicles should be equipped with noise dampening equipment to minimise disturbances. Best practice biosecurity measures should be followed, as recommended by the GB Non-Native Species Secretariat to guard against any potential for spreading invasive and non-native species during construction. Earthworks drainage should be controlled including use of temporary settlement ponds and measures will be taken to protect any temporarily exposed bare soil from runoff during heavy rainfall events. Works will be conducted in adherence to EA Pollution Prevention Guidelines (now archived) and will require a Construction Environmental Management Plan with risk assessment for pollution incidents and a response plan if occurred. Discussions with NE to agree additional mitigation measures. | Confirmation of implementation of all mitigation measures.
Biodiversity | Protected species - otter, water vole, waterbirds, macrophytes | All STT components (operation of supported or unsupported STT) - potential impacts on habitat/food availability/reproduction from changes in flow, water level or velocity, or water quality. (see STT-G2-S3-124-Protected Species Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Protected species - amphibians, birds, mammals, terrestrial invertebrates | Vyrnwy Bypass pipeline - direct impacts during construction, habitat loss and deterioration, construction air quality impacts / noise disturbance. | Best practice construction measures | Avoid construction during wintering bird period (October to March). Review pipeline routing and construction working areas during detailed design (informed by protected species survey along route). Habitat reinstatement following construction if required. Discussions with NE to agree additional mitigation measures. | Need for protected species surveys along pipeline route.
Biodiversity | Protected species - amphibians, birds, mammals, terrestrial invertebrates | Deerhurst to Culham (Interconnector) pipeline - direct impacts during construction, habitat loss and deterioration, construction air quality impacts / noise disturbance. | Best practice construction measures | Avoid construction during wintering bird period (October to March). Review pipeline routing and construction working areas during detailed design (informed by protected species survey along route). Habitat reinstatement following construction if required. Discussions with NE to agree additional mitigation measures. | Need for protected species surveys along pipeline route.
Biodiversity | Macroinvertebrate, macrophyte, and phytobenthos communities | All STT components (operation of supported or unsupported STT) - potential impacts on habitat/food availability/reproduction from changes in flow, water level or velocity, or water quality within the River Severn and River Thames. (see STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | Macroinvertebrate, macrophyte, and phytobenthos communities | All STT components (operation of supported or unsupported STT) - potential impacts on habitat availability/suitability for macrophytes and macroinvertebrates with a preference for marginal habitats (slow flowing water) within reaches of the River Avon upstream of Alveston. (see STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | No measured data to inform the risk to weir pool habitats in the River Avon
Biodiversity | INNS | Vyrnwy Direct Release / Vyrnwy Bypass pipeline - risk of spreading INNS to the River Severn from the River Vyrnwy during operational phase. (see STT-G2-S3-116-INNS Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Biodiversity | INNS | Deerhurst to Culham (Interconnector) pipeline - risk of spreading INNS to the River Severn from the River Vyrnwy during operational phase. (see STT-G2-S3-116-INNS Assessment Annex) | Operation of STT solution as defined at Gate 2 (including treatment at Deerhurst) | N/A | N/A
Biodiversity | INNS | Vyrnwy Bypass pipeline / Deerhurst to Culham (Interconnector) pipeline - increased risk of introduction of INNS though construction activities. | Best practice biosecurity measures. | N/A | N/A
Soil and Land | Harford Railway Cutting SSSI | Deerhurst to Culham (Interconnector) pipeline - site is located 650m from pipeline route and is designated for geological interest, no construction or operational impacts are anticipated. | Not applicable, no impact pathway.
Soil and Land | Lamb and Flag Quarry SSSI | Deerhurst to Culham (Interconnector) pipeline - pipeline construction related impacts, site located within 190m of pipeline route | Best practice construction methods. | Review pipeline routing and working areas during detailed design to minimise encroachment.
Soil and Land | Wainlode Cliff SSSI | All STT components (operation) - site is located adjacent River Severn, downstream of the Deerhurst intake; designated for geological interest, no construction or operational impacts are anticipated. | Not applicable, no impact pathway.
Soil and Land | Agricultural land | Vyrnwy Bypass pipeline – temporary construction impacts as pipeline route passes through grade 2 agricultural land near Oswestry and through larger areas of grade 3 land. | Best practice construction methods. | Limit extent of pipeline construction at any one time to minimise time period for soil disturbance. Review pipeline routing during detailed design to minimise encroachment.
Soil and Land | Agricultural land | Deerhurst to Culham (Interconnector) pipeline - temporary construction impacts as pipeline route passes through grade 2 agricultural land near Bishop’s Cleve, Lechlade, Hinton Waldrest, Marcham and Culham and through larger areas of grade 3 land. | Best practice construction methods. | Limit extent of pipeline construction at any one time to minimise time period for soil disturbance. Review pipeline routing during detailed design to minimise encroachment.
Soil and Land | Permitted and Historic Waste Sites: •Russell Mr C S Permitted Waste Site •Gotherington Site Historic Landfill •Kingston Bagpuize Historic Landfill •Sutton Wick No. 1 Historic Landfill •CEMEX UK Materials Ltd Permitted Waste Site | Deerhurst to Culham (Interconnector) pipeline - potential contamination risk during construction, pipeline runds adjacent Sutton Wick landfill and is within 350m of other historic/permitted sites. | Best practice construction methods. | Review pipeline routing during detailed design to minimise encroachment. Potential measures may include limiting the extent of pipeline construction at any one time will minimise the time period for soil disturbance, separation of contaminated and non-contaminated spoil, containment to prevent runoff, and containment barriers within pipeline working areas (exact requirements to be confirmed following Site Investigation). | Ground investigation
Water | WFD waterbodies: •Avon - ClaycotonYelvertoft Bk to conf R Sowe - GB109054043920 •Avon (Warks) - conf R Sowe to conf R Leam - GB109054043840 •Avon (Wark) conf R Leam to Tramway Br, Stratford - GB109054044402 •Avon- Tramway Br Stratford to Workman Br Evesham - GB109054044401 •Mary Bk - source to conf R Avon - GB109054044403 •Avon - Tolsey Lane to conf R Severn - GB109054039800 | All STT components (operation of supported or unsupported STT) - Minworth WwTW discharge diversion (transfer of water that is currently discharged into the River Tame to the River Avon) may have potential impact on migratory cues (chemical) for migratory fish species within the River Severn and tributaries. (see STT-G2-S3-122-Water Framework Directive (WFD) Assessment Annex, STT-G2-S3-112-Modelling / Physical Environment Evidence Assessment Annex, STT-G2-S3-113-Water Quality Assessment Annex, STT-G2-S3-114-Fisheries Assessment Annex and STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | Further development of operating rules | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3 For some WFD chemicals there are difficulties with commercially available limits of detection not being sufficiently low compared to EQS values. For potential olfactory inhibitors in fish, it is recognised that the commercially available limit of detection may be altogether too high to draw conclusions
Water | WFD waterbodies: •Severn - conf R Avon to conf Upper Parting - GB109054044404 •Severn (E Channel) - Horsebere Bk to Severn Est - GB109054032750 | All STT components (operation of supported or unsupported STT) - potential pass forward effects into the River Severn from the Minworth WwTW discharge diversion. (see STT-G2-S3-122-Water Framework Directive (WFD) Assessment Annex, STT-G2-S3-112-Modelling / Physical Environment Evidence Assessment Annex, STT-G2-S3-113-Water Quality Assessment Annex, STT-G2-S3-114-Fisheries Assessment Annex and STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Advanced treatment processes at Minworth WwTW and Netheridge WwTW | Further development of operating rules | Limited data on the proportionate change in load and performance efficacy and operational reliability for the planned treatment processes at Netheridge WwTW and Minworth WwTW, no cases to date in UK of reduction performance efficacy and operational reliability for the planned treatment processes. Continue to review evidence base in relation to endocrine disruptors which may act as olfactory inhibitors. Monitoring of determinands that are known to be olfactory inhibitors and/or act as endocrine disruptors to continue at the current monitoring locations to ensure that sufficient data is available to complete further modelling and assessment in Gate 3. For potential olfactory inhibitors in fish, it is recognised that the commercially available limit of detection may be altogether too high to draw conclusions
Water | WFD waterbodies: •Avon - ClaycotonYelvertoft Bk to conf R Sowe - GB109054043920 •Avon (Warks) - conf R Sowe to conf R Leam - GB109054043840 •Avon (Wark) conf R Leam to Tramway Br, Stratford - GB109054044402 | All STT components (operation of supported or unsupported STT) - potential impacts on habitat availability/suitability for macrophytes and macroinvertebrates with a preference for marginal habitats (slow flowing water) within reaches of the River Avon upstream of Alveston. (see STT-G2-S3-122-Water Framework Directive (WFD) Assessment Annex, STT-G2-S3-112-Modelling / Physical Environment Evidence Assessment Annex, STT-G2-S3-113-Water Quality Assessment Annex, STT-G2-S3-114-Fisheries Assessment Annex and STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | No measured data to inform the risk to weir pool habitats in the River Avon associated with the physical changes upstream of Alverston
Water | WFD waterbodies: •Vyrnwy - Lake Vyrnwy to conf Afon Cownwy - GB109054049880 •Afon Vyrnwy - conf Afon Cownwy to conf Afon Banwy - GB109054049720 •Afon Vyrnwy DS of Banwy confluence - GB109054049852 •Afon Vyrnwy - conf Afon Tanat to conf R Severn - GB109054049800 •Severn - conf Bele Bk to conf Sundorne Bk - GB109054049142 •Severn - Sundorne Bk to conf M Wenlock-Farley Bk - GB109054049141 •Severn conf M Wenlock-Farley Bk to conf R Worfe - GB109054049143 •Severn - conf R Worfe to conf R Stour - GB109054049145 •Severn - conf R Stour to conf River Teme - GB109054049144 •Severn - conf R Teme to conf R Avon - GB109054039760 | All STT components (operation of supported or unsupported STT) - potential changes in environmental water quality, velocity and depth during scheme operation. (see STT-G2-S3-122-Water Framework Directive (WFD) Assessment Annex, STT-G2-S3-112-Modelling / Physical Environment Evidence Assessment Annex, STT-G2-S3-113-Water Quality Assessment Annex, STT-G2-S3-114-Fisheries Assessment Annex and STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | N/A
Water | WFD waterbodies: •Thames (Evenlode to Thame) - GB106039030334 •Thames Wallingford to Caversham - GB106039030331 •Thames (Reading to Cookham) - GB106039023233 •Thames (Cookham to Egham) - GB106039023231 •Thames (Egham to Teddington) - GB106039023232 | All STT components (operation of supported or unsupported STT) - potential changes in environmental water quality, velocity and depth during scheme operation. (see STT-G2-S3-122-Water Framework Directive (WFD) Assessment Annex, STT-G2-S3-112-Modelling / Physical Environment Evidence Assessment Annex, STT-G2-S3-113-Water Quality Assessment Annex, STT-G2-S3-114-Fisheries Assessment Annex and STT-G2-S3-115-Macroinvertebrates / Other Freshwater Ecology Assessment Annex) | Operation of STT solution as defined at Gate 2 | N/A | Gate 2 hydraulic modelling of the River Thames is of limited reliability, and outcomes have been assessed with low confidence. This may have repercussions for the reliability of water quality modelling in the River Thames. The hydraulic model itself requires further work for use in Gate 3 and further flow scenarios will be required to progress the assessment made at Gate 2.
Water | WFD waterbodies: • Severn - conf Bele Bk to conf Sundorne Bk - GB109054049141 • Afon Vyrnwy - conf Afon Tanat to conf R Severn - GB109054049142 • Morda - conf unnamed trib to conf Afon Vyrnwy - GB109054049800 • Weir Bk - source to conf R Severn - GB109054049142 • Morda trib - Morton Common - GB109054049930 • Morda - source to conf unnamed trib - GB109054049930 • Childrey and Woodhill Brooks - GB106039023370 • Childrey Brook and Norbrook at Common Barn - GB106039023380 • Ock (to Cherbury Brook) - GB106039023400 • Frilford and Marcham Brook - GB106039023420 • Ock and tributaries (Land Brook confluence to Thames) - GB106039023430 • Cow Common Brook and Portobello Ditch - GB106039023360 • Letcombe Brook - GB106039023350 • Wadley Stream (Source to Thames at Duxford) - GB106039023770 • Leach (Source to Thames) - GB106039030040 • Radcot Cut - GB106039030231 • Broadwell Brook - GB106039030232 • Slade Barn Stream (Source to Windrush) - GB106039037440 • Windrush (Source to Slade Barn Stream) - GB106039037460 • Thames (Leach to Evenlode) - GB106039030333 • Thames (Evenlode to Thame) - GB106039030334 • Ginge Brook and Mill Brook - GB106039023660 • Windrush and tributaries (Little Rissington to Thames) - GB106039030440 • Sherbourne Brook - GB106039030460 • Windrush (Slade Barn Stream to Dikler) - GB106039030480 • Swilgate - source to conf R Avon - GB109054039780 • Tirle Brook - source to the conf River Swilgate - GB109054039810 • Isbourne - source to conf R Avon - GB109054039631 • Severn - conf R Avon to conf Upper Parting - GB109054044404 | Vyrnwy Bypass pipeline / Deerhurst to Culham (Interconnector) pipeline – water quality and geomorphology impacts during construction of discharge outfalls and river/stream crossings. (see STT-G2-S3-122-Water Framework Directive (WFD) Assessment Annex) | Best practice construction methods. Tunnelling under main river crossings. Minimise removal of riparian vegetation (avoid damage to bank stability, minimise habitat loss). If necessary to remove, reinstate riparian vegetation. Minimise duration of any necessary in-channel working to avoid compaction, disruption of flow processes, bank erosion Minimise impacts on water quality through temporary fluming watercourses, buffer strips, straw bales to stop sediment from the site compounds running off-site untreated. Construction mitigation relating to fine sediment runoff and spills and leaks management to be included as defined as part of any environmental permit applications and may require some route re-alignment. Where necessary timing of in river works and high noise/vibration works to avoid salmon upstream migration and spawning periods. | To include measures as set out for protected fish species above. | N/A
Water | Flood risk | Vyrnwy Bypass pipeline / Deerhurst to Culham (Interconnector) pipeline – potential for impact on flood risk during pipeline construction. | Best practice construction methods including flood compensation ponds. Tunnelling under main river crossings. | Further mitigation measures will be set out in the applications for Flood Defence Consents where these are required for the river crossing construction works. | Flood Risk Assessment
Air Quality | Local populations, in particular in the vicinity of urban areas (Oswestry, Pant and Llanymynech) | Vyrnwy Bypass pipeline – air emissions and dust from construction traffic and equipment | Best practice construction methods | Consider measures to reduce construction traffic e.g. transportation of construction materials via rail and/or water. | Desk based air quality assessment
Air Quality | Local populations, in particular in the vicinity of several urban areas and Marcham AQMA, Cheltenham Whole Borough AQMA, Abingdon AQMA, City of Oxford AQMA, Tewkesbury Town Centre AQMA | Vyrnwy Bypass pipeline – air emissions and dust from construction traffic and equipment | Best practice construction methods | Consider measures to reduce construction traffic e.g. transportation of construction materials via rail and/or water. | Desk based air quality assessment
Landscape & Visual Amenity | Cotswold AONB, South Oxfordshire Green Belt, Tewkesbury Green Belt, Vale of White Horse Green Belt | Deerhurst to Culham (Interconnector) pipeline - construction activities/removal of vegetation effects on landscape character, the setting of landscape and heritage features, the character and amenity value of views. | Best practice construction methods. | Discussions with NE to agree additional mitigation measures. | Desk based Landscape and Visual Impact Assessment
Landscape & Visual Amenity | Cotswold AONB | All STT components (operation of supported or unsupported STT) - visual impact in relation to permanent above-ground installations (limited and small in size) | Landscape planting and re-profiling will be provided to screen new infrastructure and aid integration into the landscape | Discussions with NE to agree additional mitigation measures. | Desk based Landscape and Visual Impact Assessment
Historic Environment | Listed Buildings (21 Grade I and II within 500m of the route) Conservation Areas (Oswestry) | Vyrnwy Bypass pipeline – disturbance to setting of heritage assets during pipeline construction, potential for disturbance of unknown assets. | Rerouting of pipeline to avoid known heritage assets; Best practice construction methods. | Sensitive location of construction compounds to avoid heritage assets and retain a buffer around them to be defined further in consultation with Historic England. Discussions with Historic England and the local authority to review the route alignment and working areas and agree additional mitigation measures. Monitoring by qualified staff prior and during construction as agreed in investigation programme, including recording and intervention as appropriate. | Desk based study of cultural heritage assets within and adjacent to construction works (confirmation of locations, descriptions of assets). Agreement of programme of archaeological and heritage investigation with Historic England and the local authority.
Historic Environment | Listed Buildings (three Grade II within 500m of the construction locations) Conservation Areas (Shrewsbury, Ford) Registered Park and Garden (Berwick Park) | Shrewsbury Redeployment – disturbance to setting of heritage assets during construction, potential for disturbance of unknown assets. | Best practice construction methods. | Sensitive location of construction compounds to avoid heritage assets and retain a buffer around them to be defined further in consultation with Historic England. Discussions with Historic England and the local authority to review the route alignment and working areas and agree additional mitigation measures. Monitoring by qualified staff prior and during construction as agreed in investigation programme, including recording and intervention as appropriate. | Desk based study of cultural heritage assets within and adjacent to construction works (confirmation of locations, descriptions of assets). Agreement of programme of archaeological and heritage investigation with Historic England and the local authority.
Historic Environment | Scheduled Monuments: •Gretton Church (ruins of) •Earthwork N of Lyne's Barn •Sutton Wick settlement site •Milhampost Roman site •Dixton Hill camp •Site SE of Noah's Ark Inn, Frilford •Enclosures and trackways •Ring ditches •Bowl barrow 310m SSW of Pinnock Wood Farm •Round barrow 300m west of Church Farm •Hailes Abbey and ringwork •Dovecote at Culham Manor, 110m south west of St Paul's Church Listed buildings (166 Grade I and II within 500m of pipeline route) Conservation Areas (Guiting Power, Sherbourne, Langford, Filkins and Broughton Poggs) Registered Park and Garden Grade II* (Sherbourne House) | Deerhurst to Culham (Interconnector) pipeline – disturbance to setting of heritage assets during pipeline construction, potential for disturbance of unknown assets. | Rerouting of pipeline to avoid known heritage assets; Best practice construction methods. | Sensitive location of construction compounds to avoid heritage assets and retain a buffer around them to be defined further in consultation with Historic England. Discussions with Historic England and the local authority to review the route alignment and working areas and agree additional mitigation measures. Monitoring by qualified staff prior and during construction as agreed in investigation programme, including recording and intervention as appropriate. | Desk based study of cultural heritage assets within and adjacent to construction works (confirmation of locations, descriptions of assets). Agreement of programme of archaeological and heritage investigation with Historic England and the local authority.
Population and Human Health | Local communities, including •Oswestry, Pant and Llanymynech (in proximity to Vyrnwy Bypass pipeline) •Apperley, Stoke Orchard, Gretton, Winchcombe, Naunton, Filkins, Langford (West Oxfordshire), Marcham, Drayton, Culham (in proximity to Deerhurst to Culham (Interconnector) pipeline) •Shrewsbury, Pant and Ford (in proximity to Shrewsbury Redeployment) | Vyrnwy Bypass pipeline / Deerhurst to Culham (Interconnector) pipeline / Shrewsbury Redeployment - construction noise & vibration disturbance, air quality effects. (also see Air Quality above) | Best practice construction methods. | Construction compounds to be sited sensitively and away from residential areas and along the pipeline next to a main road, so that there is least disturbance to local traffic. The hours of working associated with the construction of the treatment works, other sites and pipeline route limited to minimise amenity and environmental impacts. | Desk based noise assessment (also see Air Quality above)
Population and Human Health | Recreation, including • playing fields, public parks east of Llynclys, PRoWs including to the west of Oswestry, east of Pant, west of Maesbrook and upon approach to the discharge location in the River Severn (in proximity to Vyrnwy Bypass pipeline) •Cotswold Way, Thames Path, the Severn Way, a number of other PRoWs, two Sustrans cycle routes near Northleach and Culham, playing fields, a golf course, local parks and common land, rivers (in proximity to Deerhurst to Culham (Interconnector) pipeline) | Vyrnwy Bypass pipeline / Deerhurst to Culham (Interconnector) pipeline / Shrewsbury Redeployment - construction noise & vibration disturbance, air quality effects, temporary closures. (also see Air Quality above) | Best practice construction methods. | Consider reviewing route to avoid recreational areas. Avoid temporary closure of public rights of way and diversions. All closures to be agreed with the relevant regulators and stakeholders. Alternative routes identified if possible using existing public rights of way or public highways, with appropriate signage. Any public rights of way affected during construction to be reinstated following completion of works. Screening to be used where required in construction locations which are in proximity to public rights of way. | Desk based assessment of recreational impacts